## Slide 1
2017
2022
Today
2018
2019
2020
2021
3.5.0 Requests Finalized
May 2018
3.5.0 Candidate Release
Dec 2018
3.5.0 Final Release (NEMSIS)
Mar 2019
3.5.0 Compliance Testing begins
May 2019
3.5.0 Data acceptance starts
Aug 2019
3.5.0 Software Release (Vendor)
Feb 2020
3.5.0 Majority Implementation
Jan 2021
NASEMSO Data Managers Meeting
May 2018
NASEMSO Regional Meeting
Oct 2018
3.3.4 NEMSIS stops accepting data
Jan 1, 2019
3.4.0 NEMSIS stops accepting data
Jan 1, 2022
NEMSIS V3.5.0 Timeline developed at NEMSIS Annual Meeting 2017
OLD TIMELINE

## Slide 2
YEAR 0
YEAR 5
Today
YEAR 1
YEAR 2
YEAR 3
YEAR 4
Majority Implementation
Feb 1
v3.3.4 NEMSIS Stops Accepting Data
Sep 1
v3.4.0 NEMSIS Stops Accepting Data
Dec 31
May 1 - Aug 30
Candidate Release (NEMSIS)
4 months
Sep 1 - Nov 1
Final Release (NEMSIS)
2 months
Nov 1 - Jan 31
Compliance Testing Readiness (NEMSIS)
3 months
Feb 1 - Feb 1
Data Acceptance Readiness (NEMSIS)
12 months
Feb 1 - Feb 1
Software Release (Vendor)
12 months
Duration between release activities
TIME LINE INTERVALS APPROVED BY DMC

## Slide 3
2017
2024
Today
2018
2019
2020
2021
2022
2023
3.5.0 Requests Finalized
May 2018
3.5.0 Candidate Release
May 2019
3.5.0 Final Release (NEMSIS)
Sep 2019
3.5.0 Compliance Testing Readiness
Nov 2019
3.5.0 Data acceptance starts
Feb 2020
3.5.0 Software Release (Vendor)
Feb 2021
3.5.0 Majority Implementation
Jan 2022
NASEMSO Data Managers Meeting
May 2018
NASEMSO Regional Meeting
Oct 2018
3.3.4 NEMSIS stops accepting data
Sep 2019
3.4.0 NEMSIS stops accepting data
Jan 2023
3.5.0 Candidate Release: OLD: Dec 2018 | NEW: May 2019
3.5.0 Final Release (NEMSIS): OLD: Mar 2019 | NEW: Sep 2019
3.3.4 NEMSIS stops accepting data: OLD: Jan 2019 | NEW: Sep 2019
3.5.0 Compliance Testing Readiness: OLD: May 2019 | NEW: Nov 2019
3.5.0 Data Acceptance Starts: OLD: Aug 2019 | NEW: Feb 2020
3.5.0 Software Release (Vendor): OLD: Feb 2020 | NEW: Feb 2021
3.5.0 Majority Implementation: OLD: Jan 2021 | NEW: Jan 2022
3.4.0 NEMSIS stops accepting data: OLD: Jan 2022 | NEW: Jan 2023
Example of the Timeline Applied to Actual Dates (Timeline Already Behind by at Least 1 Month)